## Sheet1
Task | Timeframe | Deadline
Develop Concept Paper | Work in Progress
Intent to apply & RFP Guidelines sent to ORO | 1 month - 2 weeks before deadline | 2018-02-08
Meet w/ORO staff to calculate draft budget and IAF.
Meet w/School Director & Associate Dean w/project outline for feedback
Submit draft proposal to ORO for review. | Depends on the complexity of the proposal. One month to two weeks. | 2018-02-08
Finalize budget, Internal Approval form and (if applicable) provide all subcontractor/partner documents (letters of intent, budget, Scope of Work) to ORO. | 1 week before deadline | 2018-03-03
Submit final proposal documents, including budget, to ORO for additional review and follow-up.
All final documents must be submitted to ORO 3 business days prior to the sponsor deadline. | 3 days prior to deadline | 2018-03-07
Submission Deadline | Enter date as xx/xx/xxxx in red box. Day of week will be auto-provided. | 2018-03-10
| Todays Date | 2017-02-09
| Days Remaining to submission | 394
Formulas:
Deadline = [Deadline, row below]-3