Proposal for An

Early Childhood Training Institute

For the Capital Area Region

##### 7/3/99

# Submitted by
The College of Health and Human Development
Center for Prevention Research
The Pennsylvania State University
 Mark Greenberg Ph.D.
Alison Rosen M.A.
Jo Pepper M.A.
Rick Fiene Ph.D.

Proposal for An

Early Childhood Training Institute

For the Capital Area Region

I.  INTRODUCTION

At the request of the Capital Area Funders Group (CAFG), this document examines the needs, goals, structure, and initial steps for the development an early childhood training institute for the Tri-County Area.  The study was commissioned based on the perceived need for a Training Institute that would promote the social-emotional, cognitive, linguistic and physical development of the child from birth to age three.

This report proposes the center’s goals, how it will coordinate with existing resources, a plan for its administrative structure and activities, and a first year budget.  The report also suggests possible funding sources to support aspects of its operation.

The CAFG focus on young children is based on two premises:  (1) significant changes in brain organization are affected by environmental support and stimulation to infants and young children, and (2) by improving training to all person who interact with young children, we impact not only the children but also improve impact for subsequent children.

II.  GOALS OF THE STUDY

In order to develop a plan for a Early Childhood Training Institute, the following goals were identified in preparing this report:

- Examine alternative models and create benchmarks for performance.   Review and visit other developing or established centers of this kind. Utilize their experience as consultants in considering both the central goals and benchmarks of a center as well as best practices in developing such a center (See Appendix A for list of visits and consultations) .

- Assess current resources and providers.  Assess the current training resources in the Capital Area as well as the resources and interests of the current providers of training. A series of meetings with providers and professionals were held to explore current resources (See Appendix A for list of meetings).

- Assess needs and interests of consumers. As parents, child care staffs, and other related professionals would be the “target” for the training/support programs of the proposed Institute, we explored their perspectives on education and training.  A central task of the planning study was to consider training not only of traditional audiences (parent, day care providers, early childhood educators), but also training with professionals that might build new bridges in service delivery (nurses, physician’s assistants, physicians, public health providers). (See Appendix A for list of meetings).

- Consider the effect of policy changes on future training needs and opportunities. Policy changes examined included  (1) the growth of child care in the infant/toddler period, (2) the effects of welfare reform on family life, and (3) how changes in health care provide new avenues for providing education to families with infants and young children.

- Prepare final report with recommendations.  The deliverable of this project is the current report with specific recommendations for the development of the Early Childhood Training Institute.

## III.  THE IMPORTANCE OF INFANT DEVELOPMENT: WHAT WE HAVE LEARNED FROM NEUROSCIENCE AND EARLY INTERVENTION RESEARCH

The Developing Brain. Recent advances in brain research have provided great insight into how the brain, the most immature of all organs at birth, continues to grow and develop during the first years of life.  Although this growth was once thought to be determined primarily by genetics, scientists now believe that it is also highly dependent upon the child’s experiences beginning in the prenatal period. Research shows that, like protein, fat, and vitamins, interactions with other people and objects are vital nutrients for the growing and developing brain and different experiences can literally cause the brain to develop in different ways. It is this "plasticity" of the brain, its ability to develop and change in response to the demands of the environment, that enable children to be resilient in the face of change.  The baby’s experience during the first years has a determining impact on the architecture of their brain and the child’s readiness to learn and develop positive relationships with others.

How does this happen? It is believed that early experience affects how specific brain circuitry become “wired.”  Connections between neurons in the brain are the result of the production of synapses that connect the axon of one neuron to the dendrite of another. It is estimated that by age 2 a child has 1,000 trillions synapses; twice as many as adults.  By late adolescence half of these synapses have been discarded.  Thus, an important part of brain development is pruning away synapses and we now know that “use it or lose it” applies to this process.  Those neurons that are repeatedly activated in development become exempt from elimination and over time become the habits of thinking and behaving.   An critical part of this process is the development of the frontal lobe of the brain which it is the latest maturing part of the cortex and begins to develop between 8 months of age and early adolescence. This part of the brain is associated with ability to regulate and express emotions as well as to think and plan. During the infant and toddler period the ability of caregivers to help children regulate their emotions and develop healthy attachments is believed to directly influence frontal lobe development.

Although positive early experiences help the brain to develop well, poor early experiences can have devastating effects; new evidence exists that early child abuse and maltreatment can have dramatic effects on brain development and functioning leading to serious emotional difficulties.  While neuroscience research indicates the importance of early experience to brain organization, research in early social development and early intervention indicate the critical nature of early experience for social and educational outcomes.  Findings from high-quality early home-visiting and preschool intervention programs indicate that investments in supporting families and providing high quality educational/child care experience reap significant benefits to children and communities.  Unfortunately, most communities, including our own, have poor paid and often poorly trained infant and toddler child care staff and a lack of comprehensive programs to support families and infants.

Implications of Current Research.  It is now clear that the quality of experience a child experiences with parents and other caregivers in the first few years of life largely determines how her brain will develop and how she will interact with the world throughout her life.  There are a number of important implications of these findings.

- Supporting Parents.  Parents play the most important role in providing the nurturing and stimulation that children require.  It is clear they need up-to-date information and support to develop good parenting skills.  Parents with different capabilities and resources will need different levels of assistance ranging from information to regular, intensive support. More than one-third of the children in our region live in families with significant poverty and other risk factors.  It is critical that they we protect children from neglect and abuse; through home-visiting and family support programs children can receive early cognitive stimulation and improved emotional relationships that can improve their readiness for schooling.

- Creating Quality Infant and Toddler Child Care. Given the increasing numbers of infants and toddlers in child, it is critical that the care these children receive promotes their healthy growth and development. Too often, however, childcare providers are poorly trained and do not provide children with appropriate stimulation. A recent study showed that providing as little as 18 to 36 hours of high quality family day care training can increase the security of infant attachment and the quality of the childcare environment.

- Developing Community Capacity to Support Infant and Toddler Development.  Just as in the Capital Area Region, across the country there have been community-wide initiatives focused on mobilizing communities’ capacity to support infant and toddler development.  This mobilization includes the needs described above as well as advocating for state and federal support for infant and family needs, building capacity to provide adequate mental health services for parents and infants, and creating more effective linkages between parents and professionals to improve local services.  It is recognized that all adults in communities have a role to play in the development of young children.

IV.  Current status: Early Childhood Needs of the Capital Area

Through a review of the assessments and reports conducted in the three counties of Dauphin, Cumberland, and Perry, and through meetings and focus groups with professionals and parents, the following needs have emerged. See Appendix B for a summary of selected regional statistics.

Community Risks Factors. Dauphin, Cumberland, and Perry Counties all contain pockets of poverty. The three counties suffer from poverty in highly populated urban areas and in very rural areas. Both rural and urban poverty brings its own set of issues. Rural families that live in poverty are very isolated, frequently do not have reliable transportation, and have access to limited services. Urban poverty areas contain high rates of community violence, crime, and drug use.

As is typical throughout the country, both professionals and parents report a high incidence of family problems and conflict such as divorce and child or spouse abuse. These family issues are experienced by families in all three counties.  Early cognitive development of young children is hampered by dysfunctional parenting, the absence of clear parental expectations, a lack of understanding of normal child development, and failure to monitor children and keep them safe. This dysfunctional parenting may be accompanied by parental drug and alcohol abuse, or mental illness.

Lack of Services for Families with Infants and Toddlers. Services for families with young children (ages birth to three years) are very limited. Perry County has a state funded Family Center that serves 75 families with young children. Dauphin County also has two state funded Family Center that serve 200 families with young children in the area around the Hall Manor Housing Development.  Programs such as the Infant Development Program, United Cerebral Palsy, Tri County Society for Children and Adults, and the Early Intervention Program only serve young children diagnosed with a disability. There are a limited number of parenting programs that include parents with very young children such as Children’s Playroom, Escape Center, and Parents Anonymous. However, these programs do not serve families with young children exclusively.

Lack of Quality Child Care. There are many childcare slots for young children in the tri-county area. However, childcare is not affordable or accessible for all families who need it.  As reported by a recent state assessment (Iutcovich, Fiene, Johnson, Kopel, and Langan, 1997), the quality of childcare for infants and toddlers in the area is generally of low quality. This is demonstrated by the fact that there are a limited number of NAEYC Accredited Centers as of August 1998 (Dauphin County-11 [13%], Cumberland County-7 [10%], Perry County-0)

Prenatal Services, Especially for Teen Parents. There are approximately 25 school districts in the three county area. We were only able to identify two (Harrisburg and Dauphin County Technical School) that have services for teenage parents. This is a problem because the teenage pregnancy rate in Dauphin County (11.4%) is higher that the state average of 9.57%.

In the area of infant mortality, Dauphin County (1.12%) is higher that the state average of .077%. Dauphin County’s infant mortality rate is also surprisingly higher than Allegheny County (0.90%).

Fragmentation of Existing Services and Systems. Professionals in the area report that systems that serve families with young children are fragmented, many times they duplicate services, and do an inadequate job of outreach and community awareness.  Use of different terminology by different professionals is also a problem that is reported. Parents report that the above problems make access to services difficult.

Preventative Services for the Mental Health Needs of Young Children. Child abuse prevention services, parenting/nurturing training, and in home services are reported as being limited. There are few mental health professionals trained and experienced in working with very young children.  Because of the absence of mental health services options for young children, children as young as four years of age have been referred to inpatient treatment.

Training Gaps. Training in the area of infant and toddler development is limited, professionals need more training working with families in the home and in the community.  We also found that training is haphazard; that is, there is not an organized and sequenced system for care providers or professionals on the care and stimulation of infants and toddlers. There are few opportunities for education/information for new parents with infants and toddlers. Few professionals could be identified as known experts on infant and toddler development in the region.

V.  Strengths of the  Community

Although shortcomings are obvious in the needs of parents and professionals in the infant period, the Capital Area has enormous strengths on which to build such capacity. These strengths include community group interest in families, business/corporate interest in families, involvement of faith community involvement in providing services to families, a growing recognition in the public sector of the importance of early childhood development in prevention of school failure, media that are supportive of family issues.  Further, strong professional groups such as Success X Six (United Way), Capital Area Association for the Education of Young Children (CAAEYC), Pennsylvania Association for Child Care Agencies (PACCA), Pennsylvania Partnerships for Children (PPC), Pennsylvania Head Start Association (PHSA) are all located in Harrisburg.  In addition the new Harrisburg Center on Healthy Child Development has provided a locus for discussion and innovation in preventative services for young children.  Connected to this Center are a number of new initiatives including planning for coordinated systems of care, and school and community-based violence prevention.  Thus, growing public and private recognition and support of early parenting and child development provide a base of support on which to build a comprehensive program to support early child development in the region.

## VI.   Best Practices in Infant and Toddler Education

What we are learning from experts in the field of infant and toddler early childhood education is that training cannot be separated from research and advancing the field, from applied practice, or from community advocacy efforts. Examples of this include the Yale Child Study Center that has a three part mission; research, training and, clinical service. Zero to Three uses the acronym “ACT” to describe their mission; advancing the field, communication and, training and technical assistance. A training institute cannot effectively separate training from advocacy.  Legislators also need education and training in the area of early childhood education.  The Early Childhood Training Institute needs to develop a close partnership with Success By Six, Pennsylvania Association of Child Care Agencies, Pennsylvania Partnerships for Children, the Capital Area Association for the Education of Young Children  and the Pennsylvania Head Start Association. Some of these advocacy groups work at the state level but are housed in Harrisburg.

The proposed early childhood training institute will be built upon the following best practice guidelines.

- Disseminate information on recent early brain development. The importance of secure and nurturing infant and adult relationships for the cognitive development of young children should be stressed.

- Conceptualize young children and families holistically. Reinforce the belief that professionals and parents must look at children comprehensively. This means that the cognitive development of young children cannot be separated form the child’s physical and emotional development. The young child must also be looked at within the context of the child’s family.

- Two-generational programming. Support the development of programs that serve both the parents and the children, for example, health clinics or home visiting programs that provide services to both women and young children and that understand the health of the mother and the child are intertwined.

- The development of early childhood leadership. Programs cannot improve their quality without strong leadership. Local programs require assistance in upgrading their professional development programs. This includes training for program directors in the areas of management, observation, practice with feedback, and reflective supervision.

- Create a sense of “community”. Quality services for families with young children must reflect the community and be located in the communities where families live. This includes addressing the topic of culturally competent services.

# VII.  FUNCTIONS AND FOCI OF A TRAINING INSTITUTE

In order to provide a structure for planning of the Institute, it is necessary that it have (a) a set of clearly articulated functions, (2) populations of consumers that mesh with these functions, (3) a structure for staffing and oversight, (4) a proposed budget, and (5) a plan for first priorities in staging its evolution.

### A.  Functions of A Training Institute

There are five functions that are central to the mission of the Institute.

- Training.  Providing timely state-of-the-art information on infant cognitive, neurological and social development.

- Clearinghouse.  Serve as a central point for information and training on infant and toddler development for training, print, and video resources.

- Dissemination.  Disseminate information to a variety of consumer groups on infant/toddler development via print (newsletter), email, and the web.

- Advocacy. This function focuses on  “building the field “  by effectively framing the issues of the needs of infants and family. This function would focus on policy makers, the media, government leaders, foundations, etc.

- Meeting House.  Provide forums and professional development series that would create a “meeting house” for creating new partnerships and collaboration in the Capital Area.

B.  CONSUMER GROUPS IT WILL SERVE

- Parents

- Teens/Prospective Parents

- Para-professionals

- Professionals in Community (develop Prof. Organization and CE credits)

- Pre-service training (BA, MA, /Nursing Training)

C. The Matrix of Possibilities

Appendix C provide an overall matrix that integrates the proposed functions of The Institute with the goals, objectives and activities that would be conducted with different consumer groups.  Further, it suggests linkages for each activity to ongoing activities and organizations in the region.  This matrix provides “the big picture” of the long-term plan for potential Institute activities.

D.  FIRST PRIORITIES IN INSTITUTE DEVELOPMENT

This report recommends that of the numerous potential activities in the first years of the Institute, we recommend an in-depth focus on two groups: parents and child care staff.  For that reason, these foci will be elaborated below.  The matrix in the Appendix provides a brief schematic of these topics.

# A.  Parents

Presently, there is no coordinated effort among health professionals and local service providers to disseminate information to new and expectant parents about infant development (e.g. brain growth, cognitive, and social needs). Further, there is no coordinated model for parent education during the infancy/toddler period.  Finally, the Capital Area has only isolated early home visiting programs for families at-risk (currently through the Family Centers and Extension); there are no Early Head Start, Healthy Start, or Healthy Families America programs operating in the region.

Beginning Steps. The parent education initiative will begin by contacting the administrators and staffs of local hospitals to determine the feasibility of using hospitals as sites for providing parents with infant development information perinatally (using expectant parent groups) as well as during the mother's stay at the hospital.  Second, a plan will be developed for creating post-natal parent groups (in concert with hospitals, WIC and other providers). Third, the Institute will partner with local hospital and businesses to gain support for distributing monthly infant development mailers that highlight different stages of development and needs of infants/toddlers in the first two years of life.

The use of parent groups will be extended postnatally with local hospitals and existing parent groups across the region coordinating their efforts to provide parents of infants and toddlers with developmental information, effective parenting skills, and group support. This training institute will form groups of providers to discuss models of delivery and training using experienced parents as group leaders. This is an effective strategy for perpetuating parents' knowledge and interest in child development, in general, and for recruiting other parents to become group leaders.  To insure that we are reaching as many new families as possible, new parents will be targeted with the use of special geographic software that will allow us to locate areas of the tri-county where families with newborns reside.

This training institute will work with community agencies to seek state, federal, private and public support for home visitation programs for at-risk families. Currently, the tri-county area provides scattered services for at-risk families, many of whom have special issues and needs (e.g. extreme poverty and family conflict, and mental health problems).  Developing improved staff training for existing programs and forming a group of regional program directors to discuss "best practices" for training in this area will address these issues. There also is a strong need to improve the quality and access to mental health services for families with infants and toddlers since there is an absence of referral sources of qualified mental health professionals.

B. Child Care

There is a tremendous need for a new model for training infant care specialists.  One of the goals of this training institute is to develop a three county demonstration site for Pennsylvania that will develop a state-of-the-art model and system for infant toddler child care training over the next several years.  This training model would not replace or compete with current or planned training opportunities, but instead help to integrate them and thus be value-added.

This training initiative will be different from other training programs developed in the past across the Commonwealth because of the nature of infant caregiving, which is dyadic (caregiver and child) and thus not as group oriented as preschool care. To make this training effort effective, a one-on-one, mentoring relationship will be developed with programs requiring assistance.  This will be done through the efforts of infant toddler training specialists or by having staff from exemplary programs linked with programs in need.  Second, generic infant toddler workshops will be offered on common topics identified in the ongoing one-on-one mentoring sessions. Third, beginning in Year 2 (July 2000) an annual summer training institute will be held similar to the institutes held at Syracuse University and Bank Street College of Education.  It will bring caregivers and parents together along with national experts from around the country. Fourth, the institute will develop a seminar series for directors dealing with key management issues related to infant toddler programming and program administration.

### VIII.  INSTITUTE STRUCTURE

A. Sponsor

The Greater Harrisburg Foundation (GBF) will be the sponsor of the Capital Area Early Childhood Training Institute.  In its convener role, GBF was a major catalyst in developing the project. GBF also functions in all three counties, is well-known and can therefore be an effective focus for funding for the Institute from both private and governmental entities.

B. Training Provider

The operations of the Institute will be carried out by The Pennsylvania State University through the Harrisburg Center on Healthy Child Development.  This local center is part of the Prevention Research Center for the Promotion of Human Development in the College of Health and Human Development.  The Center Director is Dr. Mark Greenberg and he will be responsible for the management of center activities.

The reasons for selecting Penn State are the following: 1) Name recognition--the university is well known both locally and nationally. According to our national consultants,  the name recognition and credibility of being attached to a university is positively viewed by the general public.  This is important because a common theme in our visits was the need to be viewed by the community as being credible to deliver high quality training.;  2) Penn State is committed to helping communities improve services to children and families. The University has provided support to Dr. Greenberg to create the Harrisburg Center and Dr. Greenberg is a national leader in child development research and one of the directors of Penn State’s new Consortium on Children, Youth and Families which will further these efforts;  3) With a university base, the institute can provide both a career ladder for individuals as well as college credit for courses, workshops and other training opportunities.;  4) The university has the resources and can draw upon these resources for the requisite expertise in creating and implementing the institute;  5). A university setting provides the infrastructure for applying for and administering grants; there are numerous federal grant opportunities in this area that are limited to Universities;  6) Penn State already has the contract for the CASSP (Child and Adolescent Service System Program) Institute which is also located in Harrisburg; CASSP and the new training institute will attempt cost-sharing of space and resources.  Harrisburg is in a unique position in having a major children, youth and families initiative being created in the Harrisburg area by Penn State University.  Resources could be cross- fertilized with this training endeavor and the larger university initiative.

Two caveats might be added to placing the Institute at Penn State.  First, for any funding that is derived from community (private or public) or state sources, no overhead costs (indirect costs) would be charged; overhead on federal grants is set by individual grant announcements. Second, in order to ensure that the Institute does not become “University-focused,” a community advisory board will take an active role in setting the goals and monitoring the activities of the institute.

### C. Advisory Board

### The Institute will be supported by an ad hoc Advisory Board that will represent the major constituencies in the community that are interested in the Institute’s goals. This Board will include representatives of those organizations that have developed the Institute as well as new members. The Board will include representatives of  (1) GBF, (2) county Human Service and county government leaders, (2) local foundations, (3) local hospitals and managed care organizations, (4) providers of early services [family centers, early intervention services, Head Start, etc.], (5) parents, (6) community leaders from the Tri-County area, and (7) representatives from state government, (8) labor,  (9) the business community, and (10) Penn State University.  Representatives from Penn State will include Dr. Greenberg, and representatives from Penn State Harrisburg and the Penn State Hershey Medical School. The Board will be appointed by September 1999 and it will develop a structure of leadership and subcommittees.  As one of the first activities of the Institute will be to hire a Director, the Advisory Board will take an active role in this hiring process and its deliberations will be advisory to Dr. Greenberg.  Both Dr. Greenberg and the Director of the Institute will report to the Advisory Board.

D. Staffing

### In order to initiate the Institute’s operations a Director (1.0 FTE), an Administrative Staff (1.O FTE), and a Training Coordinator (1.0 FTE) are recommended.   Their responsibilities are detailed in the budget justification (see below).

E. Budget

It is planned that the Institute should begin operation by fall of 1999.  As such the budget presented on the next pages provides the funding needs for the Institute from October 1999 until July 1, 2000. During the fall, Dr. Greenberg will hire the Director in coordination with the input of the Advisory Board.  The director will hire the administrative assistant. As attracting a highly qualified person as Director is critical to the growth of the institute, it will be important to have on-line some assurance of multi-year funding for the core budget of the Institute.

The second budget page provides an estimated budget from July 1, 2000 until June 30, 2001 (Year 2 of the Institute).

## F. Budget Justification

Adjustments for the Year 1 Budget.  Please note that the salary levels and operations costs for the budget justification are based on a 12-month funding period. The salaries and operations budget for the period of October 1999 until June 30, 2000 has been adjusted for the shorter time period. Salaries are estimated to increase 4% per year.  Other than adjustment for the 12 month time period, there is one other substantive difference between Year 1 and Year 2.  In the Year 1 budget, there is no plan for holding an Annual Training Institute (see below for discussion); this training institute will begin in Year 2.

The Director would oversee the Capital Area Early Childhood Training Institute providing overall administrative and research guidance to the institute.  The incumbent should be an expert in the infancy and early childhood area, experience in early childhood training, experience in grant writing and a successful track record in grant support, budget and personnel management experience.  The incumbent will oversee all institute functions related to training, advocacy and research.  The incumbent will be responsible for establishing a viable training, research and fund raising program for the institute in the first year of creation and maintaining this over the long term.  The incumbent will work with local, state and federal officials in the implementation of activities for the institute.  Although staff will be hired to do the majority of training activities, the director of the institute should be the point person on all infant and toddler programming, research, and advocacy issues in south central Pennsylvania.  The incumbent will supervise all institute staff and be responsible for the budget of the institute.  Duties for the director would be the following: overall coordination and management, program start up, coordination with community groups and education agencies, outreach to foundations and funding agencies, grant writing and grant planning, budgetary oversight, coordination of information dissemination, planning and coordinating the institute's Web site, staff supervision, and liaison to Institute Board.  This person will have a doctoral or master's degree in developmental psychology, or early child development. Preference will be for a person with doctoral training.

A full time infant toddler specialist/coordinator is required because of the need to conduct intensive one on one mentoring training sessions with infant toddler staff.  This expert will be conducting the majority of trainings--both mentoring and workshops.  This person will be responsible for the training component of the institute.  This person will have a doctoral or master's degree in early child development.

A full time administrative assistant is required given the comprehensive and intensive training and information dissemination that will occur with the Institute.  The person in this position will support both the director and the coordinator of training. Duties will include secretary/clerical, meeting planning, public information, website support, budget support.

Space is estimated for a three-person suite with conference room/meeting room.  The contracted rate is based on rates paid by the CASSP Training Institute in the Office suite they occupy. We plan to co-locate (the same building, different suite) with them in order to share costs related to the training efforts.

Communication  is for all of the training opportunities as well as the web page maintenance on line.  This is for the development and dissemination of the standard print materials as well as electronic dissemination.  This will be funded through the DPW funds for all training announcements.  The Greater Harrisburg Foundation (GHF) funding will be used for general communication regarding the Institute.  This line item includes printing, phone, and postage for the above activities.

Supplies  are for all training sessions (DPW funding) and for general institute business (GHF funding).

Travel is for local travel to programs to conduct mentoring sessions and for state travel to Pittsburgh, Lehigh and York for collaborative efforts related to general infant toddler institute advocacy.

Contracted space is for space to conduct the workshop trainings and the director seminar series.

Sub-Contractors/Consultants (budget detail):

National Consultants/Mentor training/Travel		$30000

Annual Training Institute					$45000

Mentoring Sessions 						$50000

Workshops 							$18000

Web Page development & maintenance			$8000

Evaluation							$10000

TOTAL 						            $161000

All of these above costs are estimated from similar trainings conducted by either CASSP or KURC.

National consultants/Mentor training/Travel ($30000).  The national consultants   are to address state-of-the-art issues for infant toddler caregivers and parents.  Zero to Three--National Center for Infancy, Far West Lab's Program for Infant and Toddler Professional Development and the Erikson Institute for Infancy will be called in to assist in developing the overall sequence of courses and curriculum--this effort will be coordinated with the statewide DPW/KURC effort in developing a core body of knowledge for early childhood caregivers.  There will be intensive training conducted by Far West Lab for a core group of infant toddler mentors who will attend their train the trainer sessions.  Also, the selected mentors will have the opportunity to attend the Erikson Institute training sessions held throughout the year.  Zero to Three conducts training sessions that will also be available to the mentors as well.  A portion of these funds will be to cover expenses for national experts to present at the summer institute.  Consultation on the development of satellite training will come out of this line item.

Annual Training Institute ($45000) costs is associated with hotel, meals, and arrangements.  This will be a specialized training session that will combine caregivers and parents together based upon parental needs assessments related to specific training areas.  The plan is to have a summer institute for approximately 100 individuals, hopefully 50 caregivers and 50 parents would be invited to a 2-3 day summer institute in which experts from Far West Lab, Erikson Institute, and Zero to Three would work with this small group of individuals to develop a core body of knowledge for parenting education related to infant development and care.  The expectation is to develop a parent education series to be used by expectant parents in learning more about how to interact with their infants.  This series could also be used by caregivers in their respective child care programs.  Cost will cover scholarships provided to parents in order to attend this summer institute (scholarships to cover hotel and meals).  To encourage participation, no registration fee will be charged to parents or caregivers.

Mentoring sessions ($50000) will be used in which exemplary programs (mentors) are linked with programs in need.  Approximately 50% (n=25) of the programs will be conducted using this method.  The infant toddler specialist/training coordinator will conduct the other 50% (n=25).  The unit cost is based upon similar type of mentoring approaches undertaken in the KURC Child Care Training System.  This will be an intensive one-on-one training/technical assistance program.  The mentor or infant toddler specialist will spend time observing and assessing the particular program in need and will work with staff in improving the overall care provided at the site.  Generally, these mentoring relationships are approximately 40-50 hours in length.  Mentoring sessions are for center based and home based caregivers.

Workshops ($18000) will be utilized only in those situations that have been identified as a result of the one-on-one mentoring training sessions where a common theme can be addressed.  The director seminar series will also be funded out of this line item.  Fifteen-3 hour workshops for center based staff (total of 45 hours); fifteen-3 hour workshops for home based staff (total of 45 hours); fifteen-3 hour workshops (total of 45 hours)(seminar series) for directors will be provided.

Web page development ($8000) is for the services of an expert in the field to work with the infant toddler specialist in putting all infant toddler training, information about the institute, and available trainers up on the web.  This will be to develop not only an interactive web page for caregivers but for parents as well.  Instructional capabilities will also be explored by working with the World Campus at Penn State to see how classes can be offered at a distance over the web page.

Evaluation ($10000) is to determine the effectiveness of the overall training approaches.  Graduate students within the Harrisburg Center for Healthy Child Development will work with DPW and KURC evaluation teams in completing this evaluation.  A pre-test, post-test design will be utilized to determine the effectiveness of the various training modalities.  This will require on-site observations in order to determine how classroom or home practices have changed.

Staff training ($5000) is for the training coordinator and director to attend training sessions with Far West Lab, Erikson Institute, and Zero to Three related to the administration of infant training programs.

Equipment ($6000) is a one-time purchase of computer and telecommunication equipment needed for establishing the communication links via the Internet and Web page.

# In-Kind Contributions from Penn State University

Penn State is very excited about taking a partnership role with the CAFG and The Greater Harrisburg Foundation in this important initiative to positively impact young children and their families in the Capital Area.  As such, Dr. Greenberg’s time (estimated at  $15,000/year) is contributed to this project.  Further, during Year 1 of the project, Dr. Greenberg’s Prevention Research Center will contribute the cost of Rebecca Cortes (half-time) as an intern to facilitate the Center’s development and assist in its start-up. This amounts to a real-cost contribution of approximately $13,000.  In addition, following the wishes of the GHF, Penn State will not charge an indirect-cost of local funding accrued through the CAFG; however, it will receive indirect costs on federal grants as per its customary arrangement. Finally, Penn State faculty will serve as needed on the Advisory Board without fees for consultation.

Timeline

Realistically the Institute should begin operation by late fall to early winter.  A threshold level of funding of approximately $140,000 will be required by the Funders (in addition to DPW support) to get the Institute fully functioning for 12 months (until October 2000).  This level of funding will enable Penn State to hire the Director and administrative support staff and provide support funds to advertise and get promotional materials in place.  The director will need the first three months to get the institute started up and publicized and to hire an administrative assistant.  The principal investigator will hire the director in coordination with the input of the Advisory Board.  The director will hire the administrative assistant.

G.  Potential Funding Sources

Core support for the Institute will need to be derived from local, constant sources.  However, given this core support, there are numerous possibilities for state, federal, and private foundation funding.  Without core support, we do not see how it would be possible for the Institute to create a stable, long-term presence necessary to reach its goals.  It is possible that core support can be reduced by up to 50% in later years as aspects of each salaried position is at least partially covered on external grants.  Permanent endowment support should be considered as one of the options for creating long-term funding for the Institute.

### Regional

- Regional Foundations

- Regional Corporate Foundations

- County Governments

- Regional United Way Support

- Private Funders

Potential funding sources outside of the Capital Area:

### State of  Pennsylvania

- PA Department of Public Welfare: Early Childhood Initiatives

- PA Department of Public Welfare: Children’s Trust Fund

- Governor’s Project for Community Building

- PA Department of Health

- PA Governor’s Partnership for Safe Children

# Federal

1. ACYF: Early Head Start Funding

2. Other ACYF Training Opportunities

3.  Housing and Urban Development: Community Development Funds

4.  Federal Child Care Initiative Funds

### National Foundations

- Harris Foundation

- Mailman Foundation

- The WT Grant Foundation

- Foundation for Child Development

- Heinz Endowments

- William Penn Foundation

- Pew Memorial Trust

- I am Your Child (Rob Reiner Foundation)

- The Ounce of Prevention Fund

APPENDIX A

Expert Consultations

Phone Consultations

Abbey Griffen;  Zero to Three:  National Center for Infants, Toddlers, and Families

Alicia Lieberman;  University of California, San Francisco

Robert Marvin;  University of Virginia

Jude Cassidy;  University of Maryland

Rogers Kobak;  University of Delaware

Robert Harmon;  University of Colorado School of Medicine

Kathryn Barnard;  University of Washington

Outside Consultations Arranged as Visits to Capital Area

Abbey Griffen;  Zero to Three,  January 25-26

Anne Mitchell;  Wheelock College, Center for Career Development for Early Care and Education,  Feb. 10

Visits and Consultations

York Child Care Group;  2/19

Pat Levin, MaryAnn Taylor, Lorraine Weidman, Lehigh Valley Training Institute 4/6

Linda Gilkerson, Erikson Institute, Chicago 4/9

Bernice Weissbourd, Family Focus Inc., Chicago 4/9

Phyliss Glinck, Harris Foundation, Chicago 4/9

Local Group or Individual Meetings to Provide Information and Solicit Ideas

Tri County Alliance for Youth

PESSH (Partnership for Effective Seamless Services for the Homeless)

Poverty Forum

Statewide ECELS (Healthy Child Care PA)

Capital Area ICC (Interagency Coordinating Council)

Early Intervention Technical Assistance

Family Center Directors

Teen Parent Educators

Parents (working and not working)

Dauphin County MH/MR

Children’s Playroom

Harrisburg Area Community College – Roberta Bilous

Capital Area Association for the Education of Young Children (CAAEYC), Board Of Directors

Pennsylvania Child Care Association (PACCA)

Keystone University Research Corporation

PSU Medical School (Pediatrics, Family Medicine, Child Psychiatry, Nursing)

Pinnacle Health and Penn State Geisinger Women’s Healthcare Directors

Carlisle Hospital Family Birth Care Center, Monica Filburn RN

Department of Health, Maternal and Child Health, Sharon Smith

United Way of the Capital Region, Denise Calabrese

Child Care Network, Resource and Referral Coordinator, Leslie Shaw

Central Region Child Care Resouce Developers, Patty Carol

Head Start Resource and Training Center, Early Head Start Specialist, Barbara Dollar-Breshears

APPENDIX B

Summary of Child Statistics for the Capital Area of Pennsylvania

Capital Area Early Childhood Training Institute

April, 1999

|  | Dauphin County | Cumberland County | Perry County |
| --- | --- | --- | --- |
| # of licensed Child Care Centers, 1998 | 85 | 67 | 8 |
| # Registered Family Day Care Home child slots, 1998 | 4856 | 4124 | 482 |
| # NAEYC Accredited Child Care Centers, 1998 | 3 | 3 | 0 |
| # children < 18 receiving TANF, 1998 | 5011 | 566 | 255 |
| Estimated 3 children 0-3 receiving TANF | 835 | 94 | 42 |
| # children below poverty <18, 1998 | 11,086 | 3649 | 1419 |
| Estimated # children below poverty 0-3 | 1848 | 608 | 236 |
| Identified children with special needs 0-3, 1997 | 459 | 184 | 46 |
| % single parent households, 1997 | 11.3% | 6.5% | 47.6% |
| # emergency shelter placements, 1990 | 210 | 67 | 4 |
| # children served in shelters, 1997 | 456 |  |  |
| # children served in shelters 0-3, 1997 | 76 |  |  |
| % teen parents, 1998 | 11.9% | 6.31% | 8.39% |
| # children served by C & Y Agency, 96-97 | 3762 |  |  |

APPENDIX C – THE LONG-TERM GOALS AND OBJECTIVES OF THE INSTITUTE

| Target Group | Level of Service | Current Status | Goal and Objectives | Action Plan (First Steps) | Examples of Key Links to Existing Programs |
| --- | --- | --- | --- | --- | --- |
| Parents | Information | No coordinated model for timely delivery of developmental information on infant development | ### Goal Provide information to all parents on the brain growth, cognitive, and social needs of infants and toddlers ### Objectives - Work with hospitals re parent information during hospital stay (D) - Distribute Monthly information to parents in the first two years of life (D) (Mailer/video?) | - Examine models for use in hospital settings (First Steps Video – New Horizons) - Examine models for home mailers - Begin discussion with hospital administrators and staffs | 1. First Steps Video from New Horizons for Learning or Zero-To-Three - Univ of Wisconsin and PA Extension - Women’s Health Institute – Geisinger - Women’s Outpatient Healthcare-Pinnacle - Community Check Up Center - Family Birth Care Center, Carlisle Hospital |
|  | Parent Groups | A. No coordinated parents groups across the region for new parents B. Also need for training for group leaders | ### Goal Provide groups for new parents on a regular basis (bi-weekly to monthly) to provide information on parenting and support ### Objectives - Develop a plan in concert with hospitals and other deliverers of pre-natal classes (T) - Develop training program for experienced mothers to deliver such classes (T) | - Form groups of providers to discuss models of delivery - Investigate the use of GIS Coding in order to spatially locate areas of the tri-county where families with newborns reside - Examine models for training experienced parents as group leaders | - Children’s Playroom, Inc. - United Way of Capital Region (UWCR) - Capital Area Head Start - Women’s Healthcare East/ West- Pinnacle - Hospital Childbirth Classes - PA Extension - Parents Helping Parents - WIC - Family Centers |
|  | Ongoing Support/Home Visitation | Scattered services – mostly delivered through Family Centers or Early Intervention Programs | ### Goals - Develop state and federal support for home visitation programs for at-risk families for young children (Early Head Start, Nurse Home Visitation, etc.) - Develop improved staff training for current staff providing Home Visiting ### Objectives - Work with local agencies and governments to submit appropriate grants for home visitation services (G/A) - Advocate for public support for such services - Work with regional programs to help develop improved models of training for staff (A) | - Develop a system for gaining timely information on potential grants (federal/state/private) - Meet with local agencies to understand better which agencies have the capacity and interest in different grant possibilities. - Form a group of regional program directors to discuss current gaps in training and elicit their ideas about “best practices” for training | - Work with Penn State Research Offices - Develop an agenda to discuss with DPW and Center for Schools and Communities - Pittsburgh, York, Lehigh Valley Early Childhood Initiatives - PA Child Care Association - Capital Area AEYC - Pennsylvania Partnerships for Children - Capital Area Interagency Coord. Council - Healthy Child Care PA (ECELS) |
|  | Referral for Mental Health Services | Absence of referral sources of qualified mental health professionals | ### Goal Improve the quality and access to Mental Health Services for Families with Infants and Toddlers ### Objectives - Make available to community and referral sources a listing of current infant mental health specialists (D/C) - Develop a plan with local providers to attract professionals to this region who are qualified and specialized in these services (T) | - Develop a listing of current referral sources and make available to the community - Meet with local providers to build support and advocate for better infant mental health services | - Child and Adolescent Service System Program (CAASP) Institute - Central PA Psychiatric Institute - Early Intervention Technical Assistance (EITP) - Mental Health/Mental Retardation - Early Intervention Programs, Inc. |
| Teens (prior to first pregnancy) | Education | Currently insufficient focus in regional high schools on issues of parenting and child development | ### Goal Advocate for a greater focus on parenting and child development curriculum in regional high schools ### Objectives Develop a working group composed of Local Superintendents and Health/Parent Educators to assess needs and directions for action (A/P) | - Create this working group in coordination with the Capital Area Intermediate Unit Superintendents Association - Investigate existing high school curriculum models and their research efficacy | - Tri County Alliance for Youth - Teen Parent Educators – Harrisburg School District, Dauphin Co. Technical School - Community Action Program – Pregnant and Parenting Youth Program |
| Child Care Staff/ Paraprofessionals | Information | No current centralized informational source for meetings, activities | ### Goal Create a centralized information source for announcing meetings, training, activities ### Objectives - Develop a Webpage for Child Care Professionals (I) - Become a clearinghouse for regional training (C) | - Develop an accurate mailing list of current child care providers - Examine other regional training webpages to develop an effective design - Publicize the distribution of information in order to gather comprehensive information - Develop and disseminate a promotional brochure on the training institute functions. | - KURC Child Care Training Program - Capital Area AEYC - PA Head Start Association - UWCR - Childcare Network |
|  | Training | Training in infant and toddler child care issues is recognized state-wide as being in need of significant improvement. This is also reflected in the Capitol Area | ### Goal Create a coordinated sequence of training for child care staff working with infants and toddler ### Objectives - Design a coordinated sequence of training for child care staff (with support from Zero-To-three) (P/G) - Apply for state funding to conduct regional training (G) - Develop a registry of qualified trainers in PA. (C) - Advocate for improved training (A) - Hold an annual summer training institute. (T) - Conduct a seminar series for directors. (T) - Explore the development of infant toddler satellite training series. (T) | - Make application to KURC for state child care training funds (completed 4/99). - Sub contract with Zero to Three on developing coordinated sequence of training. - Collaborate with the KURC Early Childhood Professional development work group developing core body of knowledge in PA. Develop core competencies for infant and toddler caregivers. - Set up data base for trainers, cross check with KURC training data base. - Work with Zero to Three and Erickson Institute on developing plan for advocating for high quality training. - Begin organizing for summer institute--arranging national speakers, site selection, needs assessment for topics, etc. - Inventory infant program directors on the development of seminar series. - Begin discussions with Jim Van Horn related to developing an infant toddler satellite training series. - Development and dissemination of child care training brochures for the three county area. | - PA Child Care Association - Harrisburg Area Community College - Penn State Univ. - Bank Street College - WestEd, Center for Child and Family Studies - Pittsburgh, York, Lehigh Valley initiatives - CAASP Institute - Child Care Resource Developer, Sub Region 3 - Head Start Quality Improvement Center; Early Head Start, Region 3 |
| Professionals in the Community (B.A./M.A./M.D., etc) | Training | There is no coordinated set of trainings for professionals working with parents and young children | ### Goal Develop ongoing training for professionals working with parents and infants in education, health, mental health, and social service | - Conduct needs assessment of professionals in three county area regarding their training needs. - Inventory training resources in the three county area. - Contact professional organizations regarding what they have to offer and what their ongoing CEU requirements are. See what pertains to infant and toddler area. | - UWCR - CAAEYC - Institute Advisory Board - CAASP - KURC Child Care Training - Central PA Psychiatric Institute |

Institute Functions

(D) – Disseminate Information

(T)  – Training

(A) – “Building the Field”/Advocacy

(P) – Planning

(G) – Grant Writing

(C) – Clearninghouse

(M) – Meeting House

Bibliography

Anderson, S., & Messick, S. (1974). Social competence in young children. Developmental Psychology, 10, 282-293.

Annie E. Casey Foundation. (1995). The path of most resistance: Reflections on lessons learned from new futures. Baltimore, MD: Author.

Barnett, S. W. (1993a). Benefit-cost analysis of preschool education: Findings from a 25-year follow-up. American Journal of Orthopsychiatry, 63, 500-508.

Barnett, W. S. (1985). The Perry Preschool Program and its long-term effects: A benefit-cost analysis. High/Scope Early Childhood Policy Papers, No. 21. Ypsilanti, MI: High/Scope Educational Research Foundation.

Barnett, W. S. (1995). Long-term effects of early childhood programs on cognitive and school outcomes. The Future of Children, 5, 25-50.

Barrera, M. E., Rosenbaum, P. L., & Cunnigham, C. E. (1986). Early home intervention with low-birth-weight infants and their parents. Child Development, 57, 20-23.

Belsky, J. (1984). The determinants of parenting: A process model. Child Development, 55, 83-96.

Belsky, J. (1993). Etiology of child maltreatment: A developmental-ecological analysis. Psychological Bulletin, 114, 413-434.

Blair, C., Ramey, C. T., & Hardin, J. M. (1995). Early intervention for low birthweight, premature infants: Participation and intellectual development. American Journal of Mental Retardation, 99, 542-554.

Breakey, G., & Pratt, B. (1991). Healthy growth for Hawaii's “Healthy Start”: Toward a systematic statewide approach to the prevention of child abuse and neglect. Zero to Three, 16-22.

Bronfenbrenner, U. (1979). The ecology of human development: Experiments by nature and design. Cambridge, MA: Harvard University Press.

Brooks-Gunn, J., Gross, R. T., Kraemer, H. C., Spiker, D., & Shapiro, S. (1992). Enhancing the cognitive outcomes of low birth weight, premature infants: For whom is the intervention most effective. Pediatrics, 89, 1209-1215.

Brooks-Gunn, J., Liaw, F., & Klebanov, P. K. (1992). Effects of early intervention on cognitive function of low birth weight preterm infants. Journal of Pediatrics, 120, 350-359.

Brooks-Gunn, J., McCormick, M. C., Shapiro, S., Benaisch, A., & Black, G. W. (1994). The effects of early education intervention on maternal employment, public assistance, and health insurance: The Infant Health and Development Program. American Journal of Public Health, 84, 924-931.

Carnegie Task Force on Meeting the Needs of Young Children. (1994). Starting points: Meeting the needs of our youngest children. New York: Carnegie Corporation of New York.

Children's Defense Fund. (1995). The state of America's children yearbook: 1995. Washington, DC: Author.

Cochran, M. (Ed.). (1993). International handbook of child care policies and programs. Westport, CN: Greenwood Press.

Comer, J. P. (1988). Educating poor minority children. Scientific American, 259, 42-48.

Conduct Problems Prevention Research Group. (1992). A developmental and clinical model for the prevention of conduct disorders: The FAST Track Program. Development and Psychopathology, 4, 509-527.

Crockenberg, S. (1981). Infant irritability, mother responsiveness, and social influences on the security of infant-mother attachment. Child Development, 52, 857-865.

Damasio, A. R. (1994).  Descartes’ error:  Emotion, reason, and the human brain.  New York:  Grosset/Putnam.

Dawson, G. (1994).  Frontal electroencephalographic correlates of individual differences in emotion expression in infants:  A brain systems perspective on emotion.  In N. Fox (Ed.), Monographs of the society for research in child development:  Vol. 59, The development of emotion regulation:  Biological and behavioral considerations (pp. 135-151).

Dawson, G. , Panagiotides, H., Klinger, L. G., & Hill, D. (1992)  The role of frontal lobe functioning in the development of infant self-regulatory behavior.  Brain and Cognition, 20, 152-175.

Dawson, G., Hessl, D., & Frey, K. (1994).  Social influences on early developing biological and behavioral systems related to risk for affective disorder.  Development and Psychopathology, 6, 759-779.

Dryfoos, J. G. (1994). Full-service schools: A revolution in health and social services for children, youth, and families. San Francisco, CA: Jossey-Bass.

Dunst, C. J., Trivette, C. M., & Thompson, R. B. (1990). New directions for family resource and support programs. In D. G. Unger & D. R. Powell (Eds.), Families as nurturing systems: Support across the life-span (pp. 19-44). New York: Haworth Press.

Falkner, F., & Tanner, J. M. (1978).  Human Growth.  NY:  Plenum.

Fenichel, E., (1992) Learning through Supervision and Mentorship to  Support the Development of Infants, Toddlers and their Families. Washington, DC: Zero to Three.

Fox, N. A. (1994).  Dynamic cerebral processes underlying emotion regulation.  In N. Fox (Ed.), Monographs of the society for research in child development:  Vol. 59.  The development of emotion regulation:  Biological and behavioral considerations (pp. 152-166).

Goldsmith, H. H., & Campos, J. J. (1982).  Toward a theory of infant temperament.  In R. N. Emde, & R. J. Harmon (Eds.), The development of attachment and affiliative systems.  New York:  Plenum.

Goleman, D. (1995).  Emotional intelligence.  New York:  Bantam Books.

Gomby, D. S., Larner, M. B., Stevenson, C. S., Lewit, E. M., & Behrman, R. E. (1995).  Long-term outcomes of early childhood programs: Analysis and recommendation. The Future of Children, 5, 6-24.

Gomby, D. S., Larson C. S., Lewit, E. M., & Behrman, R. E. (1993). Home visiting: Analysis and recommendations. The Future of Children, 3, 6-22.

Greenberg, M. T., & Crnic, K. A. (1988). Longitudinal predictors of developmental status and social interaction in premature and full-term infants at age two. Child Development, 59, 554-570.

Greenberg, M. T., Kusche, C. A., & Speltz, M. (1991). Emotional regulation, self-control, and psychopathology: The role of relationships in early childhood. In D. Cicchetti & S. L. Toth (Eds.), Rochester symposium on developmental psychopathology, Vol. 2: Internalizing and externalizing expressions of dysfunction (pp. 21-56). Hillsdale, NJ: Erlbaum.

Greenberg, M. T., Speltz, M. L., & DeKlyen, M. (1993). The role of attachment in the early development of disruptive behavior problems. Development and Psychopathology, 5, 191-213.

Greenough, W. T., Black, J. E., & Wallace, C. S. (1987). Experience and brain development. Child Development, 58, 439-459.

Greenspan, S. I., & Greenspan, N. T. (1985).  First feelings.  New York:  Viking.

Greenwood, P. W., Model, K. E., Rydell, C. P., & Chiesa, J. (1996). Diverting children from a life of crime: Measuring costs and benefits. Santa Monica, CA: RAND, MR-699-UCB/RC/IF.

Hamburg, D. A. (1992). Today's children: Creating a future for a generation in crisis. New York: Times Books.

Haskins, R. (1989). Beyond metaphor: The efficacy of early childhood education. American Psychologist, 44, 274-283.

Hawaii State Department of Health. (1992). Healthy Start: Hawaii’s system of family support services. Report to the 16th Legislature, State of Hawaii.

Hawkins, J. D., Catalano, R. F., & Brewer, D. D. (1995). Preventing serious, violent and chronic juvenile offending: Effective strategies from conception to age 6. In J. C. Howell, B. Krisberg, J. J. Wilson, & J. D. Hawkins (Eds.), A sourcebook on serious, violent, and chronic juvenile offenders (pp. 47-60). Newbury Park, CA: Sage.

Hernandez, D. J. (1995). Changing demographics: Past and future demands for early childhood programs. The future of children, 5(3), 145-160.

Horacek, H. J., Ramey, C. T., Campbell, F. A., Hoffman, K. P., & Fletcher, R. H. (1987). Predicting school failure and assessing early intervention with high-risk children. Journal of the American Academy of Child and Adolescent Psychiatry, 36, 758-763.

Infant Health and Development Program. (1990). Enhancing the outcomes of low-birth-weight, premature infants: A multisite, randomized trial. Journal of the American Medical Association, 263, 3035-3042.

Institute of Medicine. (1994). Reducing risks for mental disorders: Frontiers for preventive intervention research. Washington, DC: National Academy Press.

Johnson, D. L., & Walker, T. B. (1987). Primary prevention of behavior problems in Mexican-American children. American Journal of Community Psychology, 15, 375-386.

Johnson, D. L., & Walker, T. B. (1991a). A follow-up evaluation of the Houston Parent-Child Development Center: School performance. Journal of Early Intervention, 15, 226-236.

Karr-Morse, R. & Wiley, M. S. (1998)  Ghosts from the Nursery : Tracing the Roots of Violence

Knitzer, J., & Aber, J. L. (1995). Young children and poverty: Facing the facts. American Journal of Orthopsychiatry, 65, 174-176.

Lally, R., J., Mangione, P. L., & Honig, A. S. (1988). The Syracuse University Family Development Research Program: Long-range impact on an early intervention with low-income children and their families. In D. Powell (Ed.), Parent education as early childhood intervention: Emerging directions in theory, research, and practice (pp. 79-104). Norwood, NJ: Ablex.

Lazar, I., Darlington, R. B., Murray, H., Royce, J., & Sniper, A. (1982). Lasting effects of early education: A report from the Consortium for Longitudinal Studies. Monographs of the Society for Research in Child Development, 47 (2-3, Serial No. 195).

LeDoux, J. E. (1995).  Emotion:  Clues from the brain.  Annual Review of Psychology, 46, 209-235.

Lerner, R. M. (1994). America's children and youth in crisis. Thousand Oaks, CA: Sage.

Levenstein, P. (1992). The Mother-Child Home Project: Research methodology and the real world. In J. McCord & R. E. Tremblay (Eds.), Preventing antisocial behavior (pp. 43-66). New York: Guilford.

McKey, R. H., Condelli, L., Ganson, H., Barrett, B. J., McConkey, C., & Planz, M. C. (1985). The impact of Head Start on children, families and communities (DHHS Publication No. OHDS 85-31193). Washington, DC: U.S. Government Printing Office.

National Commission on Children. (1991). Beyond rhetoric: A new American agenda for children and families. Washington, DC: U.S. Government Printing Office.

Nurcombe, B., Howell, D. C., Rauh, V. A., Teti, D. M., Ruoff, P., & Brennan, J. (1984). An intervention program for mothers of low birthweight infants. Journal of the American Academy of Child Psychiatry, 23, 319-325.

Olds, D. L. (1988). The prenatal/early infancy project. In R. H. Price, E. L. Cowen, R. P. Lorion, & J. Ramos-McKay (Eds.), Fourteen ounces of prevention: A casebook for practitioners (pp. 9-23). Washington, DC: American Psychological Association.

Olds, D. L. (1995, April). Studies of prenatal and infancy nurse home visitation. Presented at the Society for Research in Child Development, Indianapolis, IN.

Olds, D. L., & Kitzman, H. (1993). Review of research on home visiting for pregnant women and parents of young children. The Future of Children, 3, 53-92.

Olds, D. L., Henderson, C. R., & Kitzman, H. (1994). Does neonatal and infancy nurse home visitation have enduring effects on qualities of parental caregiving and child health at 25 to 50 months of life? Pediatrics, 93, 89-98.

Olds, D. L., Henderson, C. R., Chamberlin, R., & Tatelbaum, R. (1986). Preventing child abuse and neglect: A randomized clinical trial of nurse home visitation. Pediatrics, 78, 65-78.

Olds, D. L., Henderson, C. R., Kitzman, H., & Cole R. (1995). Effects of prenatal and infancy nurse home visitation on surveillance of child maltreatment. Pediatrics, 95, 365-372.

Olds, D. L., Henderson, C. R., Phelps, C., Kitzman, H., & Hanks, C. (1993). Effects of prenatal and infancy nurse home visiting on government spending. Medical Care, 31, 155-174.

Pierson, D. E. (1988). The Brookline Early Education Project. In R. H. Price, E. L. Cowen, R. P. Lorion, & J. Ramos-McKay (Eds.), Fourteen ounces of prevention: A casebook for practitioners (pp. 24-31). Washington, DC: American Psychological Association.

Powell, D. R. (1994). Evaluating family support programs. In S. L. Kagan & B. Weissbourd (Eds.), Putting Families First: America’s family support movement and the challenge of change (pp. 441-470). San Francisco: Jossey-Bass.

Provence, S., & Naylor, A. (1983). Working with disadvantaged parents and children: Scientific issues and practice. New Haven, CT: Yale University Press.

Ramey, C. T., & Campbell, F. A. (1987). The Carolina Abecedarian Project: An educational experiment concerning human malleability. In J. J. Gallagher & C. T. Ramey (Eds.), The malleability of children (pp. 127-140). Baltimore: Brookes Publishing.

Ramey, C. T., & Ramey, S. L. (1993). Home visiting programs and the health and development of young children. The Future of Children, 3, 129-139.

Ramey, C. T., Bryant, D. M., Campbell, F. A., Sparling, J. J., & Wasik, B. H. (1988). Early intervention for high-risk children: The Carolina Early Intervention Program. In R. H. Price, E. L. Cowen, R. P. Lorion, & J. Ramos-McKay (Eds.), Fourteen ounces of prevention: A casebook for practitioners (pp. 32-43). Washington, DC: American Psychological Association

Ramey, C. T., Bryant, D. M., Wasik, B. H., Sparling, J. J., Fendt, K. H., & LaVange, L. M. (1992). Infant Health and Development Program for low birth weight, premature infants: Program elements, family participation, and child intelligence. Pediatrics, 89, 454-465.

Sameroff, A. J., & Seifer, R. (1990). Early contributors to developmental risk. In J. Rolf, A. S. Masten, D. Cicchetti, K. H. Neuchterlein, & S. Weintraub (Eds.), Risk and protective factors in the development of psychopathology. New York: Cambridge University Press.

Schore, A.  (1994).  Affect regulation and the origins of the self:  Neurobiology of emotional development.  Hillsdale, NJ:  Erlbaum.

Schorr, L. B. (1988). Within our reach: Breaking the cycle of disadvantage. New York: Anchor Press.

Schweinhart, L. J., & Weikart, D. P. (1989). The High/Scope Perry Preschool Study: Implications for early childhood care and education. Prevention in Human Services, 7, 109-132.

Schweinhart, L. J., Barnes, H. V., & Weikart, D. P. (1993). Significant benefits: The High/Scope Perry Preschool Study through age 27. Ypsilanti, MI: High/Scope Press.

Seitz, V. & Apfel, N. H. (1994). Effects of a school for pregnant students on the incidence of low-birth weight deliveries. Child Development, 65, 666-676.

Seitz, V. (1991). Intervention programs for impoverished children: A comparison of educational and family support models. Annals of Child Development, 7, 73-103.

Seitz, V., & Provence, S. (1990). Protective factors in individual resilience. In S. J. Meisels & J. P. Shonkoff (Eds.), Handbook of early childhood intervention (pp. 400-427). New York: Cambridge University Press.

Seitz, V., Rosenbaum, L. K., & Apfel, N. H. (1985). Effects of family support intervention: A ten-year follow-up. Child Development, 56, 376-391.

Shore, R.  (1997)  Rethinking the Brain:  New Insights into Early Development,  New York: Families and Work Institute.

Sroufe, L. A. (1979).  Socioemotional development.  In J. D. Osofsky (Ed.), Handbook of infant development.  New York:  Wiley.

Stern, D. (1985).  The interpersonal world of the infant.  New York:  Basic Books.

Sylwester, R. (1995).  A celebration of neurons:  An educator’s guide to the human brain.  Alexandria, VA:  Association for Supervison and Curriculum Development.

Thatcher, R. W. (1994).  Psychopathology of early frontal lobe damage:  Dependence on cycles of development.  Development and Psychopathology, 6, 565-596.

Walker, T., & Johnson, D. L. (1988). A follow-up of the Houston Parent-Child Development Center: Intelligence test results. Journal of Genetic Psychology, 149, 377-381.

Wasik, B. H., Ramey, C. T., Bryant, D. M., & Sparling, J. J. (1990). A longitudinal study of two early intervention strategies: Project CARE. Child Development, 61, 1682-1692.

Weiss, H. B. (1993). Home visits: Necessary but not sufficient. The Future of Children, 3, 113-128.

Weissbourd, B. (1994). The evolution of the family resource movement. In S. L. Kagan & B. Weissbourd (Eds.), Putting families first: America's family support movement and the challenge of change (pp. 28-47). San Francisco: Jossey-Bass.

Werner, E. E., & Smith, R. S. (1982). Vulnerable but invincible: A study of resilient children and youth. New York: McGraw-Hill.

Zero to Three,  National Center for Infants, Toddlers, and Families, April/May 1998, Volume 18 No. 5

Zigler, E. & Berman, W. (1983). Discerning the future of early childhood intervention. American Psychologist, 38, 894-906.

Zigler, E. (1994). Reshaping early childhood intervention to be a more effective weapon against poverty. American Journal of Community Psychology, 22, 37-48.

Zill, N., & Nord, C. W. (1994). Running in place: How American families are faring in a changing economy and an individualistic society. Washington, DC: Child Trends.

Zill, N., & Rogers, C. C. (1988). Recent trends in the well-being of children in the United States and their implications for public policy. In A. J. Cherlin (Ed.), The changing American family and public policy (pp. 31-115). Washington, DC: The Urban Institute Press.

Ectireport799